## Sheet1
|  |  | 2014 |  | 2014 |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
16th Tisza Group meeting | bar: 2019 Q3; 2020 Q3
DEVELOPMENT OF Policy documents, technical reports, studies, databases |  | Related Action
Joint Document with the ICPDR |  | ALL | bar: 2014 Q1 to 2014 Q4
Update of the Danube Basin Analysis Report |  | A1M3 | bar: 2014 Q1 to 2014 Q3
2nd Danube River Basin Management Plan |  | A1M4, A3M1, A3M4 | bar: 2014 Q1 to 2015 Q4
Alignment of Funding (A1M2) |  | A1M2 | bar: 2014 Q1 to 2014 Q2
Development of the Danube Delta Sub-basin Analysis Report |  | A2M5 | bar: 2014 Q1 to 2014 Q4
Development of the Danube Delta Management Plan |  | A2M6
Development of Prut Management Plan |  | A2M7 | bar: 2014 Q1 to 2015 Q1
Development of the 2nd ITRBMP |  | A2M4
Finalisation and approval of the first Sava River Basin Management Pan |  | A2M10 | bar: 2014 Q1 to 2014 Q4
Update of the Sava Basin Analysis Report |  | A2M9 | bar: 2014 Q1 to 2014 Q4
Development of the 2nd Sava River Basin Management Plan: First step development and finalisation of the Significant Water Management Issues (SWMI) paper |  | A2M10 | bar: 2014 Q1 to 2015 Q2
Examination of the biodiversity and environment status of sediment, water and biota in the Sava River Basin |  | A10M7
Establishment and completion of the Sava GIS |  | A3M5 | bar: 2014 Q1 to 2015 Q2
Joint Danube Survey 3 (Final Technical Document) (survey held in 2013) |  | A3M2 | bar: 2014 Q1 to 2014 Q4
Survey of the situation of buffer zones |  | A5 M1 | bar: 2014 Q1 to 2015 Q3
Survey of the situation on management of solid waste in small rural settlements |  | A5M3 | bar: 2014 Q1 to 2015 Q3
Survey of the situation on alternative collection and treatment wastewater in small rural settlements |  | A5M4 | bar: 2014 Q1 to 2015 Q3
Situation toward legislate at the appropriate level to limit the presence of phosphates in detergents - Policy response on the overview report |  | A7M2 | bar: 2014 Q1 to 2015 Q3
Feasibility study on early warning water quality monitoring |  | A2M4 | bar: 2014 Q1 to 2015 Q3
WORKSHOPS, TECHNICAL MEETINGS (not exhaustive list)
Workshop with ICPDR on P free ban – participate in the organisation of the WS |  | A7M1,M2,M3 | bar: 2016 Q1
Workshop of the ICPDR on HYMO |  | A10M5 | bar: 2014 Q1 to 2015 Q2
Ceremonial Tisza office opening event |  | A2M3 | bar: 2014 Q4 to 2015 Q1
Tisza project preparatory meeting (back to back with the 21st TG mtg) |  | A2M3,M4 | bar: 2014 Q4 to 2015 Q1
Sediment project preparatory meetings |  | A10M4 | bar: 2014 Q3 to 2014 Q4
Participation on relevant ICPDR meetings, workshops |  | ALL
Workshop “Water Sources Protection” - April 2015, Bratislava (farmers, industries and waste water treatment plants) |  | A11M3, A12M5 | bar: 2015 Q2
World Water Day - block od presentations devoted to Danube Strategy |  | A12M5 | bar: 2015 Q1
Conference “Drinking Water” - presentation of safeguarding of drinking water supply |  | A12M6 | bar: 2015 Q4
PA4 discussion on ongoing activities with EU representatives (when needed, e.g. meeting with representatives of EU Funds)
Any other:
MANAGEMENT ACTIVITIES
Organisation of SG meetings |  | ALL | bar: 2014 Q1; 2014 Q4 to 2015 Q1; 2015 Q3; 2016 Q1; 2016 Q3; 2017 Q1; 2017 Q3; 2018 Q1; 2018 Q3; 2019 Q1; 2019 Q3; 2020 Q1; 2020 Q3
ICPDR&PA4 meetings |  | ALL | bar: 2014 Q3; 2015 Q1; 2016 Q1; 2017 Q1; 2018 Q1; 2019 Q1; 2020 Q1
Development of the Joint ICPDR-EUSDR PA4 workplan and timetable (living document - continuous update in the frame of the SGs) |  | ALL | bar: 2014 Q4 to 2015 Q1; 2015 Q3; 2016 Q1; 2016 Q3; 2017 Q1; 2017 Q3; 2018 Q1; 2018 Q3; 2019 Q1; 2019 Q3; 2020 Q1; 2020 Q3
Facilitating START program - project proposal development | bar: 2014 Q2 to 2014 Q3; 2015 Q2 to 2015 Q3
Project developements incl. the organisation of preparatory meetings (also linked to management activities) - partner searching events |  | ALL | bar: 2014 Q1 to 2017 Q4
Any other: |  | ALL
DISSEMINATION ACTIVITIES (not exhaustive list)
Brochure on the document of Alignment of Funding |  | A1M2, A12M5
Dissemination brochure on the achievement of the PA4/ICPDR/ISRBC (interview or articles from each organisations on the main activities relevant from the EUSDR implementation point of view) |  | ALL
Brochure on projects ongoing related to PA4 (progress and results) |  | Where relevant | bar: 2014 Q4 to 2015 Q1; 2016 Q4 to 2017 Q1
Participation of PACs in relevant Conferences and seminars etc. |  | Where relevant
Publication in EUSDR website (e.g. detailed information on available funds in connection to EUSDR activities) |  | Where relevant
To reprint the brochure on PA 4 activities in English |  | Where relevant | bar: 2015 Q1
To print A4 folder for papers with the motive of PA4 EUSDR |  | Where relevant | bar: 2015 Q1
Article to the Water Management Journal - Effective and sustainable utilization of water sources |  | A11M2 | bar: 2015 Q1
Publication in Danube Watch Magazine, and ICPDR website (e.g. detailed information on available funds in connection to EUSDR activities) |  | ALL
Project activities - CORE projects (Observership and participating in project meetings)
Sediment project (with PA5) - proposal develoment and implementation |  | A10M4 | bar: 2014 Q4 to 2018 Q4
Tisza Project - proposal develoment and implementation |  | A2M3, M4, A3M3 | bar: 2014 Q4 to 2018 Q4
Feasibility study for restoring continuity at the Iron Gate dams (responsible Romania and Serbia with the support from the ICPDR) - PA4 woul be ready to facilitate the activity |  | A10M3 | bar: 2014 Q1 to 2017 Q4
Project activities - RELEVANT projects / project ideas
Ongoing project: SEE-River |  | A2 | bar: 2014 Q1 to 2014 Q4
Ongoing project: ICZM (Coastal Zone) |  | A14
Ongoing project: CC-Ware |  | A12 | bar: 2014 Q1 to 2014 Q4
Finished project: Cross - border Water Supply Development in the Pannon-Fertő Region (Finished in 2013) |  | A13
Finished project: CC-Waters (Finished in 2012) |  | A13
Finished project: Liberty Island project (WWF-HU - finished in 2014) |  | A13 | bar: 2014 Q1 to 2014 Q2
Planned project (consortium already set up): Blue Danube |  | A4
Planned project (consortium already set up): FoWaP |  | A13
Planned project (consortium already set up): SEWABIS |  | A2
Project idea: Joint Tisza Survey |  | A3M3
LEGEND
Ongoing ICPDR activity relevant from EUSDR PA4 point of view
ICPDR and PA4 joint action
Ongoing ISRBC activity relevant from EUSDR PA4 point of view
PA4 specific activity
finalisation of an action(target deadline)
continuous activity
? | Exact date to be further specified
SK- comments
Notes:
Deadine are target deadlines
Under discussion
Background studies are already available related to this topics. Discussion has already been started between ICPDR and PA4 on how to further develop this specific issues. By the 9th SG meeting (in 2015) proposal will be introduced regarding the next step related to this activities
START Project proposal is submitted
TBD
START Projekt proposal is submitted
Ongoing activity
START Projekt proposal is submitted
Exact dates under discussion