## Project Data Sheet
PROJECT DATA SHEET EU STRATEGY FOR THE DANUBE REGION. PILLAR 2. PRIORITY AREAS 4, 5, 6
A - Project Status
1. Project title (long title and acronym, if any)
Sa(f)veDROP - Strengthening Transnational Water Resilience through Integrated Management of Water Scarcity in Danube River Basin Resources under Emerging Contaminants Pressures
2. Main Priority Area and Action under Pillar 2 to which the project idea is to be submitted to
PA 4.06 Promote measures to adapt to climate change impacts in relation to water quality and quantity
3. Other Priority Areas and Actions under Pillar 2 the project is contributing to (please select three at maximum). In case the project adresses also other Priority Areas, please list them in field 19.
PA 4.01 Promote monitoring, prevention and reduction of water pollution deriving from hazardous and emerging substances (EU priority substances and watch list candidates as well as Danube basin specific pollutants candidates and others e.g. micro plastics-plastics, pharmaceuticals, PFOS)
PA 4.07 Enhance cooperation, increase and exchange knowledge and secure financing to water quality measures in the Danube Region
PA 4.04 Promote measures aimed at reducing knowledge deficits related to protecting water resources and safe guarding drinking water supply
4. Current Project Phase
Project in preparation (e.g. project proposal, feasability study)
B - Project description
5. Project relevance (Please outline the relevance and necessity from a macro-regional perspective. What are the benefits of the project for the implementation of the EUSDR?)
Water quality deterioration is a critical climate change consequence causing socio-economic & macroregional pressures demanding transnational, cross-sectoral solutions. National frameworks against droughts & emerging contaminants (EOCs) are fragmented, hindering basin-wide coordination, monitoring, water quality & quantity assessment. Sa(f)veDROP supports EUSDR, closing knowledge gaps via harmonized drought-condition monitoring, assessing scarcity hotspots, pollution sources & integrating findings in Danube Watch List of basin-aligned drought-relevant EOCs, guiding prioritization under scarcity conditions. Sa(f)veDROP Navigator decision support tool strengthens evidence-based, transnational DRB water resilience. Knowledge and Networking Hub enables cross-sectoral cooperation via stakeholder dialogues & policy briefs. Supporting EUSDR emphasis on cross-border cooperation, non-EU countries (BiH, ME, RS, UA) are involved as PP/ASP, strengthening neighborly relations.
6. Project general and specific objectives
Sa(f)veDROP strengthens transboundary cooperation, knowledge exchange & capacity building for management of water bodies facing scarcity & climate change-driven EOCs impacts in DRB. By piloting monitoring, mitigation measures, decision support tool & tailored capacity-building, project enhances cross-sectoral cooperation, policy harmonization & resilience under drought & low-flow conditions.
7. Proposed project activities and their location(s). (Please list main and sub-activities). The most part of the project, its activities and its related impacts should be located in the Danube Region.
Assessing quanti- & qualitative water status in pilots -Monitoring in 9 DRB countries (BG, BiH, CZ, DE, ME, HR, HU, RS, SI) -Danube Watch List Building DRB resilience: transferring knowledge & good practices -Synthesis report & webinars on current state, policy & legislation on droughts, scarcity, EOCs -Catalogue of existing water management strategies -Knowledge & Networking Hub -Guidelines & international training for EOCs sampling in low- & high-flow regimes -National policy roundtables & water resilience workshops -Joint water resilience policy briefs -Transnational conferences -Cross-sectoral networking Sa(f)veDROP Navigator: data to decision making -Water quality & quantity risk databases -Decision support tool & capacity building workshops -Practical steps to water resilient DRB
8. Expected results and outcomes (Please use measurable indicators, where available.)
3 solutions for capacity building and policy alignment across DRB related to droughts, water scarcity & EOCs: - Danube Watch List - Sa(f)veDROP Navigator - decision-making support tool - Water Resilience Knowledge & Networking Hub Jointly implemented monitoring for EOCs in drought conditions - 9 pilot action areas
9. Target groups (Who is affected by the project results, who will use the project results?)
Wide range of stakeholders from policy makers (national, regional and local authorities), water operators and providers, scientific community, education centres and schools, general public, hospitals and medical centres such as institutes of public health, EGTC such as Tisza European Grouping of Territorial Cooperation Limited Liability, cross-border legal bodies (EUSDR and ICPDR), Intergovernmental Panel on Climate Change, Common Implementation Strategy Working Group on Groundwater
10. Project timeframe (foreseen starting and ending date in mm/yy. If not available mention the duration in number of months)
30 months: 01/07/2026 - 31/12/2028
C - Links to other Programmes/Policies
11. Link with other projects or actions already undertaken (if relevant please list the project title, acronym, name of Lead Partner, status of the project: financed, under implementation, closed, planned to be submitted, etc.)
DriDanube (closed, Slovenian Environment Agency), Danube Water Balance (ongoing, OVF), DanubeHazard m3c (closed, TUW), D-CLEAN (ongoing, GWPCEE), MicroDrink (ongoing, HGI-CGS), Tethys (ongoing, TUW), boDEREC-CE (closed, HGI-CGS), FramWat (closed, Szkoła Główna Gospodarstwa Wiejskiego w Warszawie), ADAPTisa (closed, Faculty of Technical Sciences in Novi Sad), InDiMaND (ongoing, Budapest Firefighter Association), ICPDR, EUSDR, Clim4Cast (ongoing, Global Change Research Institute), JOINTISZA (closed, OVF), SWIM (ongoing, O.M. Offshore Monitoring Limited), SaveWater (ongoing, Ústav výzkumu globální změny AV ČR), Cli OP Thaya (closed, Amt der Niederösterreichischen Landesregierung / Gruppe Wasser), DALIA (ongoing, OVF), InnoWATCCH (ongoing, OVF), TRANSFER Danube (ongoing, National Meteorological Administration). Sa(f)veDROP partnership is involved on several of these initiatives, fostering knowledge exchange & avoiding duplication of efforts.
12. Relevant international/EU directives and national legislation the project addresses (e.g. Water Framework Directive, EU Biodiversity Strategy). Also connections to relevant international organisations (e.g. ICPDR, WWF, Carpathian Convention) should be mentioned here.
Strong connections will be fostered with EUSDR (Action Plan) & ICPDR (DRBMP, Joint Programme of Measures, JDSs, DanubeHIS). Project will contribute to EU Green Deal, Territorial Agenda 2030, Oct 2025 EU Council & Parliament provisional agreement to update list of priority substances for surface & groundwaters, UN SDGs, Water Resilience Strategy 2025, DWD, GWD, WFD, EU Chemicals Strategy, Environment Action Programme (EAP) to 2030, SRBMP & ITRBMP, Paris Agreement, DRPC.
D - Project Budget and Funding
13. Approximate total project budget (in EUR)
2.100.000 EUR
14. Potential sources of funding (if appropriate, indicate funding programme and specific call, as well as the amount of own sources available)
The proposed project will be submitted to the third call for proposals within the Interreg Danube Region Programme 2021 - 2027.
E - Partnership and Contact
15. (Proposed) Lead Partner (Responsible institution/body)
Croatian Geological Survey (HGI-CGS), Department of Hydrogeology and Engineering Geology, Croatia
16. Contact details of responsible person (Letter of Recommendation shall be sent to)
Ana Selak Croatian Geological Survey aselak@hgi-cgs.hr +385 1 6160 704
17. Project Partners (Name and country, Status committed to be involved / already involved)
University of Ljubljana, Slovenia, confirmed University of Belgrade, Faculty of Mining and Geology, Serbia, confirmed Institute of Public Health, Federation Bosnia and Herzegovina, confirmed Friedrich-Alexander-Universität Erlangen-Nürnberg, Germany, confirmed T. G. Masaryk Water Research Institute, Czech Republic, confirmed Bulgarian Water Association, Bulgaria, confirmed Middle Tisza District Water Directorate, Hungary, confirmed Centre for Ecotoxicological Research, Montenegro, confirmed
18. Project Partner wanted (please specify type and country / region of partners you are looking for)
-
F - Closing remarks
19. Any other information considered relevant (e.g. information on predecessor project, resubmissions and reasons for rejection, status of project development, information on project meetings, public relations, involvement of policy making bodies etc.)
The project is a follow-up of Interreg CE boDEREC-CE and Interreg DRP MicroDrink, expanding to also address the challenges of droughts and water scarcity in relation to EOCs contamination. The project is in proposal stage, will undergo MA/JS review and be submitted by December 15th 2025. Project meetings will be held in five countries (HR, RS, DE, CZ, SI), targeted workshops will be conducted in all partner countries (BG, BiH, CZ, DE, HR, HU, ME, RS, SI) and webinars will be online and open-access to all. External communication will be heavily implemented within project activities, through five newsletters, joint water resilience policy briefs, online news on project website and social media channels, press releases, conferences, etc. Policy and decision making bodies and key water operators will be involved through national stakeholder workshops, targetted questionnaires, policy roundtables, cross-sectoral networking exchange visits, etc. The project also contributes to PA 4.03 Promote prevention and reduction of diffuse pollution, promote nutrient retention, smart irrigation and water reuse, foster and develop an active process of dialogue and cooperation between authorities responsible for agriculture and environment to ensure that measures are taken to address diffuse pollution and ensure smart water use.
G - For PAC use only - Result of Assessment and Steering Group Decision
PA 4.01 Promote monitoring, prevention and reduction of water pollution deriving from hazardous and emerging substances (EU priority substances and watch list candidates as well as Danube basin specific pollutants candidates and others e.g. micro plastics-plastics, pharmaceuticals, PFOS)
PA 4.02 Continue boosting major investments in building, upgrading, maintaining and rehabilitating urban wastewater treatment facilities and promote alternative collection and treatment of wastewater in small rural settlements, including measures to build capacity at the regional and local levelacross the Danube basin
PA 4.03 Promote prevention and reduction of diffuse pollution, promote nutrient retention, smart irrigation and water reuse, foster and develop an active process of dialogue and cooperation between authorities responsible for agriculture and environment to ensure that measures are taken to address diffuse pollution and ensure smart water use
PA 4.04 Promote measures aimed at reducing knowledge deficits related to protecting water resources and safe guarding drinking water supply
PA 4.05 Promote measures to enable fish migration in the Danube River basin
PA 4.06 Promote measures to adapt to climate change impacts in relation to water quality and quantity
PA 4.07 Enhance cooperation, increase and exchange knowledge and secure financing to water quality measures in the Danube Region
PA 5.01 Provide sufficient support for development and execution of risk management plans for different hazards
PA 5.02 Enhance the capacities, extend the coverage of basin-wide or regional forecasting and warning systems, and develop rapid response procedures
PA 5.03 Strengthen disaster prevention and preparedness among governmental and non-governmental organizations
PA 5.04 Decrease human impacts that evolves natural risk factors resulting in environmental damages
PA 5.05 Anticipate regional and local impacts of climate change
PA 6.01 Establish transnational cooperation and harmonisation of the strategic
PA 6.02 Build capacities of national and local authorities, non-governmental organisations, expert and scientific community in the environment related matters
PA 6.03 Develop and/or implement conservation action plans and/or management plans for endangered umbrella species of the Danube Region
PA 6.04 Promote research to develop and apply the most appropriate methods for prevention and control of IAS and for management of the priority pathways in line with the DIAS Strategy and IAS Regulation (EU) 1143/2014
PA 6.05 Anchoring the concept of EU green infrastructure in the Danube Region
PA 6.06 Promote ecological connectivity through cooperation between macroregional strategies
PA 6.07 Enhance and/or maintain soil-related ecosystem services
PA 6.08 Identify locations with obsolete pesticide and similar chemical remains and prepare a remediation plan and a risk management plan in the case of environmental accidents
PA 6.09 Take measures to gradually reduce air pollution, with as a minimum step to respect the limit values for pollutants according to the Air Quality Directive
PA 6.10 Stimulate the management and the ecological restoration of wetlands, particularly in the Danube delta
Project Idea
Project in preparation (e.g. project proposal, feasability study)
Project currently under implementation, on-going
Project completed, already finished
Steering Group decision: Project will be awarded with Label
Steering Group decision: Project will not be awarded with Label
Steering Group decision: Project has potential, but needs to be further developed